## Slide 1
PROJ 216 Software Project Concepts
Day 3

## Slide 2: Day 3 Agenda
Project Scheduling
An overview of MS Project
Team & Client Relationship Issues
Project Communication
Other documents produced during the project
Work on MS-Project Gantt chart – due 8 a.m. Day 4

## Slide 3: Scheduling the Project
On Time Within Budget: Software Project Management Practices and Techniques, Third Edition by E.M. Bennatan ISBN:0471376442 Chapter 11

## Slide 4: Scheduling the Project
Breaking the project down
  Phases 1, 2, 3…
  Sub-Phases or summary tasks 1.1, 1.2, 1.3…
  Tasks 1.1.1, 1.1.2, 1.1.3,…
  Milestones
    Can have deliverables
    Zero time duration
Phase, sub-phase, task hierarchy is called the Work Breakdown Structure (WBS)

## Slide 5: Scheduling the Project
Gantt Chart
  Plots timeline using bars
  Most commonly used chart
See: http://www.netmba.com/operations/

## Slide 6: Scheduling the Project
Critical Path Method (CPM)
  Diagram charts tasks and estimated duration time
  Tasks are related by predecessor/successor constraints
  Allows determination of which tasks are critical to success of project
  The critical path is the shortest time it will take to complete the project
  https://www.youtube.com/watch?v=SF53ZZsP4ik

## Slide 7: Class Exercise
You have been asked to complete project in the shortest time possible. The next slide show the tasks, their predecessors, and duration in days
Which tasks belong to the critical path?
For each task, determine its float
What is the float for all tasks on the critical path?

## Slide 8: Tasks for Class Exercise
Task | Duration | Predecessor(s)
A | 2 | None
B | 2 | None
C | 1 | None
D | 4 | A
E | 5 | B
F | 1 | C, D
G | 6 | A, E
H | 4 | F
I | 7 | G, H

## Slide 9
0 0
0 0
A 2
B 2
C 1
D 4
E 5
F 1
G 6
H 4
I 7
Done
Go
0 1
7 8
0 2
2 4
0 2
0 2
2 6
4 8
6 7
8 9
7 11
9 13
2 7
2 7
7 13
7 13
13 20
13 20
20 20
20 20
7
2
2
2
2
5
5

## Slide 10: Scheduling the Project
Schedule
  Tasks
    Relationships: 1) finish to start. 2) finish to finish. 3) start to finish. 4) start to start.
  Time estimates
  Resource allocation
  Lead time can start B 2 days before A finish
  Lag time B can start 2 days after A finish
A
B
A
B

## Slide 11: Scheduling the Project
More Terminology
  Baseline
  Predecessor
  Successor
  Constraints
    Start no later than, Finish no later than, Must start on, Must finish on, etc.

## Slide 12: Scheduling the Project
Cost
  Kinds of costs
  Estimating
    Who should do it?
    Fixed price vs. hourly rates
  Tracking completion status & actual vs. estimates
    Slippage
  http://www.dummies.com/careers/project-management/how-to-estimate-project-costs/
  http://www.projectmanagementdocs.com/project-documents/activity-cost-estimates.html#axzz4PSD1CxgJ

## Slide 13: Estimating Task Duration
Mathematical method (PERT weighted average)
  Determine optimistic time for task, most likely time, pessimistic time
  Sample formula:
  Estimate = (optimistic + (4 * most likely) + pessimistic) / 6
History
Experience

## Slide 14: Scheduling the Project
Microsoft Project demo

## Slide 15: Managing Teams and Clients
Chapter 7 - Contractors and Clients Developing Effective Websites: A Project Manager's Guide by Roy Strauss and Patrick Hogan
Chapter 13 - Managing Customers and Beneficiaries Complex IT Project Management: 16 Steps to Success by Peter Schulte

## Slide 16: Dealing with Problems
Four main causes of wasted project time
  Vague or conflicting project definition and scope
  Lack of clearly articulated expectations
  Competing (and shifting) priorities
  No process established for problem resolution and feedback
  New Directions in Project Management by Paul C. Tinnirello (ed), Chapter 38
    ISBN:084931190X

## Slide 17: Dealing with Problems
What do you do if the project slips behind?
  Reschedule?
  More resources?
  Overtime or adding shifts?
  Use subcontractors?
  Shift resources from non-critical tasks to critical tasks?
  Make tasks concurrent instead of sequential if possible?
  Change scope by eliminating or simplifying tasks?
  Change scope of critical tasks to shorten them?

## Slide 18: Group Exercise
Using the document “Team & Client Conflict Situations”, get into groups and brainstorm solutions to the 3 conflict scenarios. Class discussion will follow.

## Slide 19: Project Communication
Purpose of Status Reports
  Review status
  Compare data
  Check progress on the schedule
  Check resource utilization
  Check budget status
  Watch for any potential problems looming in the future
  Help stakeholders make decisions affecting the project

## Slide 20: Project Communication
Contents of Status Reports
  From
  To
  Date
  Time period covered
  Potential problems (things to watch out for)
  Activities during the reporting period
  Activities planned for next reporting period
  Problems/issues

## Slide 21: Project Communication
Change Control -- Data Captured
    Change-Request ID
    Change Type -- new requirement, enhancement, defect
    Date Submitted/Date Updated
    Title -- One-line summary of the proposed change
    Description
    Originator Priority -- low, medium, or high
    Team Priority --low, medium, or high
    Originator
    Modifier -- person responsible for implementing the change
    Verifier -- person who is responsible for verifying the change
    Project
    Response/Solution/Status

## Slide 22: Project Communication
Problem reports/ bug reports
  Forms or software
  A Guide to Software Configuration Management by Alexis Leon Chapter 8

## Slide 23: Presentations
Chapter 13 - Managing Customers and Beneficiaries “Complex IT Project Management: 16 Steps to Success” by Peter Schulte
  The Dynamics of Public Presentations
http://www.ted.com/talks/amy_cuddy_your_body_language_shapes_who_you_are

## Slide 24: Gantt Chart Assignment
Working in Project groups, determine the breakdown of the Threaded project into phases and identify some tasks for Phase 1, task relationships, and estimated durations.
Prepare a Gantt chart using MS-Project (one copy per group)
  Make tasks auto-scheduled, and include predecessor/successor relationships wherever applicable
  Assign resources (people) to tasks; make sure that no resources are overscheduled
  Make sure that your Gantt chart includes at least one summary task and at least one milestone
Each students submits: due 8 a.m. Day 4